## JOSE ANTONY MUTHU
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Jose Antony Muthu S | 11.12.2017 | 10:45 AM to 4:00 PM | Absent
2 | Jose Antony Muthu S | 12.12.2017 | 10:45 AM to 4:00 PM | Absent
3 | Jose Antony Muthu S | 13.12.2017 | 10:45 AM to 4:00 PM | Absent
4 | Jose Antony Muthu S | 14.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | In Progress
5 | Jose Antony Muthu S | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | In Progress
Saturday
Sunday
6 | Jose Antony Muthu S | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Jose Antony Muthu S | 19.12.2017 | 10:45 AM to 4:00 PM | Absent
8 | Jose Antony Muthu S | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | In Progress
9 | Jose Antony Muthu S | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Jose Antony Muthu S | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress
Saturday
Sunday
Monday
11 | Jose Antony Muthu S | 26.12.2017 | 10:45 AM to 4:00 PM | Absent
12 | Jose Antony Muthu S | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress

## AKSHAYA
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Akshaya | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Akshaya | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Akshaya | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Akshaya | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Akshaya | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
Saturday
Sunday
6 | Akshaya | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | In Progress
7 | Akshaya | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Akshaya | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | In Progress
9 | Akshaya | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Akshaya | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Prgress
Saturday
Sunday
Monday
11 | Akshaya | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress
12 | Akshaya | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress

## MOHANAKRISHNAN
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Mohana Krishnan S | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Mohana Krishnan S | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Mohana Krishnan S | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Mohana Krishnan S | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Mohana Krishnan S | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
Saturday
Sunday
6 | Mohana Krishnan S | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | In Progress
7 | Mohana Krishnan S | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Mohana Krishnan S | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | In Progress
9 | Mohana Krishnan S | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Mohana Krishnan S | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Prgress
Saturday
Sunday
Monday
11 | Mohana Krishnan S | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress
12 | Mohana Krishnan S | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress

## JEYA SUNDARI
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Jeya Sundari G | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Jeya Sundari G | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Jeya Sundari G | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Jeya Sundari G | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Jeya Sundari G | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
Saturday
Sunday
6 | Jeya Sundari G | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | In Progress
7 | Jeya Sundari G | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Jeya Sundari G | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | In Progress
9 | Jeya Sundari G | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Jeya Sundari G | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Prgress
Saturday
Sunday
Monday
11 | Jeya Sundari G | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress
12 | Jeya Sundari G | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | In Progress