## JOSE ANTONY MUTHU
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Jose Antony Muthu S | 11.12.2017 | 10:45 AM to 4:00 PM | Absent
2 | Jose Antony Muthu S | 12.12.2017 | 10:45 AM to 4:00 PM | Absent
3 | Jose Antony Muthu S | 13.12.2017 | 10:45 AM to 4:00 PM | Absent
4 | Jose Antony Muthu S | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Jose Antony Muthu S | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
|  | Saturday |  | Holiday
Sunday
6 | Jose Antony Muthu S | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Jose Antony Muthu S | 19.12.2017 | 10:45 AM to 4:00 PM | Absent
8 | Jose Antony Muthu S | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Jose Antony Muthu S | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Jose Antony Muthu S | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
|  | Saturday |  | Holiday
Sunday
Monday
11 | Jose Antony Muthu S | 26.12.2017 | 10:45 AM to 4:00 PM | Absent
12 | Jose Antony Muthu S | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Jose Antony Muthu S | 28.12.2017 | 10:45 AM to 4:00 PM | Learning Angular Js and Spring Framework | Completed
14 | Jose Antony Muthu S | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Jose Antony Muthu S | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Jose Antony Muthu S | 02.01.2018 | 10:45 AM to 4:00 PM | Absent
17 | Jose Antony Muthu S | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Jose Antony Muthu S | 04.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
19 | Jose Antony Muthu S | 05.01.2018 | 10:45 AM to 4:00 PM | Absent
|  | Saturday |  | Holiday
Sunday
20 | Jose Antony Muthu S | 08.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
21 | Jose Antony Muthu S | 09.01.2018 | 10:45 AM to 4:00 PM | Learning ireport | Completed
22 | Jose Antony Muthu S | 10.01.2018 | 10:45 AM to 4:00 PM | Working on Sample ireport | Completed
23 | Jose Antony Muthu S | 11.01.2018 | 10:45 AM to 4:00 PM | JDBC connectivity in iReports | Completed
Holiday
24 | Jose Antony Muthu S | 17.01.2018 | 10:45 AM to 4:00 PM | Generating iReports | Completed
25 | Jose Antony Muthu S | 18.01.2018 | 10:45 AM to 4:00 PM | First Review
26 | Jose Antony Muthu S | 19.01.2018 | 10:45 AM to 4:00 PM | Learning JASON | In Progress

## AKSHAYA
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Akshaya | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Akshaya | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Akshaya | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Akshaya | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Akshaya | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
Saturday
Sunday
6 | Akshaya | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Akshaya | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Akshaya | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Akshaya | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Akshaya | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
Saturday
Sunday
Monday
11 | Akshaya | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
12 | Akshaya | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Akshaya | 28.12.2017 | 10:45 AM to 4:00 PM | Absent
14 | Akshaya | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Akshaya | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Akshaya | 02.01.2018 | 10:45 AM to 4:00 PM | Grid UI design | Completed
17 | Akshaya | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Akshaya | 04.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
19 | Akshaya | 05.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
|  | Saturday |  | Holiday
Sunday
20 | Akshaya | 08.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
21 | Akshaya | 09.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
22 | Akshaya | 10.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
23 | Akshaya | 11.01.2018 | 10:45 AM to 4:00 PM | UI Design -Module 3 | In Progress
Holiday
24 | Akshaya | 17.01.2018 | 10:45 AM to 4:00 PM | UI Design -Module 3 | In Progress
25 | Akshaya | 18.01.2018 | 10:45 AM to 4:00 PM | First Review
26 | Akshaya | 19.01.2018 | 10:45 AM to 4:00 PM | UI Design -Module 3 | In Progress

## MOHANAKRISHNAN
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Mohana Krishnan S | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Mohana Krishnan S | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Mohana Krishnan S | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Mohana Krishnan S | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Mohana Krishnan S | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
Saturday
Sunday
6 | Mohana Krishnan S | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Mohana Krishnan S | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Mohana Krishnan S | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Mohana Krishnan S | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Mohana Krishnan S | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
Saturday
Sunday
Monday
11 | Mohana Krishnan S | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
12 | Mohana Krishnan S | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Mohana Krishnan S | 28.12.2017 | 10:45 AM to 4:00 PM | Learning Angular Js and Spring Framework | Completed
14 | Mohana Krishnan S | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Mohana Krishnan S | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Mohana Krishnan S | 02.01.2018 | 10:45 AM to 4:00 PM | Grid UI design | Completed
17 | Mohana Krishnan S | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Mohana Krishnan S | 04.01.2018 | 10:45 AM to 4:00 PM | Absent(placement drive)
19 | Mohana Krishnan S | 05.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
|  | Saturday |  | Holiday
Sunday
20 | Mohana Krishnan S | 08.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
21 | Mohana Krishnan S | 09.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
22 | Mohana Krishnan S | 10.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
23 | Mohana Krishnan S | 11.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls | In Progress
Holiday
24 | Mohana Krishnan S | 17.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls | In Progress
25 | Mohana Krishnan S | 18.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls
26 | Mohana Krishnan S | 19.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls | In Progress

## JEYA SUNDARI
NSURE Motor Policy Inssuance System
S.no | Name | Date | Time | Project Task | Status
1 | Jeya Sundari G | 11.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
2 | Jeya Sundari G | 12.12.2017 | 10:45 AM to 4:00 PM | Domain knowledge | Completed
3 | Jeya Sundari G | 13.12.2017 | 10:45 AM to 4:00 PM | Refreshing Basics Java | Completed
4 | Jeya Sundari G | 14.12.2017 | 10:45 AM to 4:00 PM | Zeroth Review
5 | Jeya Sundari G | 15.12.2017 | 10:45 AM to 4:00 PM | Installing and Configuring Development Tool | Completed
Saturday
Sunday
6 | Jeya Sundari G | 18.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Angular JS | Completed
7 | Jeya Sundari G | 19.12.2017 | 10:45 AM to 4:00 PM | Executing Sample Java Project | Completed
8 | Jeya Sundari G | 20.12.2017 | 10:45 AM to 4:00 PM | Learning Basics of Spring Framework | Completed
9 | Jeya Sundari G | 21.12.2017 | 10:45 AM to 4:00 PM | Absent
10 | Jeya Sundari G | 22.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
Saturday
Sunday
Monday
11 | Jeya Sundari G | 26.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
12 | Jeya Sundari G | 27.12.2017 | 10:45 AM to 4:00 PM | Learning Spring Framework | Completed
13 | Jeya Sundari G | 28.12.2017 | 10:45 AM to 4:00 PM | Learning Angular Js and Spring Framework | Completed
14 | Jeya Sundari G | 29.12.2017 | 10:45 AM to 4:00 PM | Absent(placement drive)
15 | Jeya Sundari G | 30.12.2017 | 10:45 AM to 4:00 PM | Absent
|  | Sunday |  | Holiday
Monday
16 | Jeya Sundari G | 02.01.2018 | 10:45 AM to 4:00 PM | Grid UI design | Completed
17 | Jeya Sundari G | 03.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
18 | Jeya Sundari G | 04.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
19 | Jeya Sundari G | 05.01.2018 | 10:45 AM to 4:00 PM | UI Design-Module 1 | Completed
|  | Saturday |  | Holiday
Sunday
20 | Jeya Sundari G | 08.01.2018 | 10:45 AM to 4:00 PM | Absent
21 | Jeya Sundari G | 09.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
22 | Jeya Sundari G | 10.01.2018 | 10:45 AM to 4:00 PM | UI Design and controls -Module 1 | Completed
23 | Jeya Sundari G | 11.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls | In Progress
Holiday
24 | Jeya Sundari G | 17.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls | In Progress
25 | Jeya Sundari G | 18.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls
26 | Jeya Sundari G | 19.01.2018 | 10:45 AM to 4:00 PM | Dashboadr controls | In Progress